## Sheet1
2009/10 FOCUS COURSE CATALOG UPDATING
|  |  | (Content, Design and Production Schedule) |  |  |  | 2009-02-06
Responsibility Keys: | [6 empty] | C. O'Donnell
CC = Content Coordinators
AM = Account Mangers
GD = Graphic Designer
CNS = Computer & Network Services
PROJECT STEPS |  | GRAD CATALOGS |  | Responsibility |  | UG CATALOG |  | Responsibility
[5 empty] | # Days |  |  |  | # Days
FOCUS TRAINING for CC |  | Friday, Feb. 6 |  | CN&S | 1 hour | Wed. March 4 |  | CN&S | 1 hour
(Library Lab 115: 11-12 or 2-3 PM)
Catalog MS Docs to CC |  | 2009-02-16 |  | AM |  | 2009-03-23 |  | AM
Content Updating |  | 2/16/09 - 3/13/09 |  | CC | 20 days | 3/23/09 - 4/18/09 |  | CC | 20 days
Deadline #1 for Content Updating |  | 2009-03-13 |  | CC |  | 2009-04-18
CN&S Upload to Database |  | 2009-03-16 |  | CN&S | 1 day | 2009-04-20 |  | CN&S | 1 day
Graphic Design - Rough Draft #1 |  | 3/1709 - 4/3/09 |  | GD & AM | 14 days | 4/21/09 - 5/15/09 |  | GD & AM | 20 days
Catalog Draft #1 to CC (PDF) |  | 4/6/09 - 4/17/09 |  | CC | 9 days | 5/18/09- 6/1/09 |  | CC | 12 days
Deadline #2 for Content Updating: |  | 2009-04-17 |  | CC |  | 2009-06-01 |  | CC
CN&S Upload #2 to Database |  | 2009-04-20 |  | CN&S | 1 day | 2009-06-02 |  | CN&S | 1 day
Graphic Design - Rough Draft #2 |  | 4/21/09-4/30/09 |  | GD & AM | 8 days | 6/3/09-6/12/09 |  | GD & AM | 8 days
Catalog Final Draft #2 to CC (PDF) |  | 5/1/09-5/11/09 |  | CC | 7 days | 6/15-6/30/09 |  | CC | 12 days
Deadline: Final for Content |  | 2009-05-11 |  | CC |  | 2009-06-30
Final Design and Review |  | 5/12-5/28/09 |  | GD & AM | 12 days | 7/1-7/17 |  | GD & AM | 12 days
Send Off for Printing |  | 2009-06-01 |  | GD |  | 2009-06-20 |  | GD
Delivery | Due Date | 2009-07-01 |  |  |  | 2009-08-20